## Sheet1
Activity Name | Activity ID | Planned duration | Planned Start date | Planned End date | Predecessor | TPV | TAC | Percentage of completion | TEV | Actual Duration | Actual Start date | Actual End date
1.1 | Control account/work package 1 | 1000 | 500 | 500 | 2000 |  | 1000 | 500 | 500 |  | 500 | 500
1.2 | Control account/work package 2 |  | 500 | 500 | 800 | 900 |  | 500 | 500 |  | 500 | 500
1.3 | Control account/work package 3 |  |  |  | 700 | 2000
1.4 | Control account/work package 4 |  |  |  | 200 | 600
1.5 | Control account/work package 5
1.6 | Control account/work package 6
Planned Value
Activity Name | Activity ID | Budget at Completiom |  | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 |  | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12
1.1 | Control account/work package 1 | 3500 |  | 1000 | 500 | 2000
1.2 | Control account/work package 2 | 4200 |  |  | 500 | 800 | 900 | 2000
1.3 | Control account/work package 3 | 4500 |  |  |  | 700 | 2000 | 1000 |  | 800
1.4 | Control account/work package 4 | 3300 |  |  |  | 200 | 600 | 1000 |  | 1500
1.5 | Control account/work package 5 | 3000 | [5 empty] | 700 |  | 500 | 1000 | 800
1.6 | Control account/work package 6 | 6700 | [9 empty] | 700 | 2000 | 1000 | 2000 | 1000
| Budget at Completion | 25200 |  | 1000 | 1000 | 3700 | 3500 | 4700 |  | 2800 | 1000 | 1500 | 2000 | 1000 | 2000 | 1000
|  | Cummulative Planned Value (PV) |  | 1000 | 2000 | 5700 | 9200 | 13900 |  | 16700 | 17700 | 19200 | 21200 | 22200 | 24200 | 25200
Actual Cost
Activity Name | Activity ID | Period 1 |  | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 |  | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12
1.1 | Control account/work package 1 | 800 |  | 250 | 1500
1.2 | Control account/work package 2 |  |  | 900 | 700 | 1200 | 1700
1.3 | Control account/work package 3 |  |  |  | 300 | 300 | 1250 | 1500
1.4 | Control account/work package 4 |  |  |  | 100 | 500 | 900 | 700 |  | 400
1.5 | Control account/work package 5 | [5 empty] | 400 | 600 |  | 500
1.6 | Control account/work package 6
| Actual cost | 800 |  | 1150 | 2600 | 2000 | 4250 | 2800 |  | 900 | 0 | 0 | 0 | 0 | 0
| Cummulative Actual costs (AC) | 800 |  | 1950 | 4550 | 6550 | 10800 | 13600 |  | 14500 | 14500 | 14500 | 14500 | 14500 | 14500
Percentage of completion
Activity Name | Activity ID | Budget at Completiom |  | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 |  | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12
1.1 | Control account/work package 1 | 3500 |  | 15% | 50% | 100% | 100% | 100% |  | 100% | 100%
1.2 | Control account/work package 2 | 4200 |  |  | 25% | 30% | 60% | 75% |  | 90% | 100%
1.3 | Control account/work package 3 | 4500 |  |  |  | 25% | 40% | 50% |  | 100% | 100%
1.4 | Control account/work package 4 | 3300 | [5 empty] | 25% |  | 80% | 90%
1.5 | Control account/work package 5 | 3000 | [7 empty] | 25% | 75%
1.6 | Control account/work package 6 | 6700 | [8 empty] | 50%
Cummulative Earned Value (EV)
Activity Name | Activity ID | Budget at Completiom |  | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 |  | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12
1.1 | Control account/work package 1 | 0 |  | 525 | 1750 | 3500 | 3500 | 3500 |  | 3500 | 3500
1.2 | Control account/work package 2 | 0 |  |  | 1050 | 1260 | 2520 | 3150 |  | 3780 | 4200
1.3 | Control account/work package 3 | 0 |  |  |  | 1125 | 1800 | 2250 |  | 4500 | 4500
1.4 | Control account/work package 4 | 0 | [5 empty] | 825 |  | 2640 | 2970
1.5 | Control account/work package 5 | 0 | [7 empty] | 750 | 2250
1.6 | Control account/work package 6 | 0 | [8 empty] | 3350
|  | Cummulative Earned Value |  | 525 | 2800 | 5885 | 7820 | 9725 |  | 15170 | 20770 | 0 | 0 | 0 | 0 | 0